## Sheet2
Phase 1: Initial Setup & Basic Features
Task | Sub-Task | Start Date | End Date | Duration (Days)
Project Setup and Architecture Design | Set up repositories, CI/CD pipelines, project structure |  |  | 3
| Choose tech stack (frontend, backend, database) |  |  | 3
| Define user roles and permissions in the architecture |  |  | 3
| Configure project management tools (Jira, Trello, etc.) |  |  | 3
Login System Development | Design login page (UI/UX) |  |  | 2
| Implement backend login functionality (email/password) |  |  | 2
| Implement session management (JWT/cookies) |  |  | 2
| Implement "Remember Me" functionality |  |  | 2
| Basic validation & error handling |  |  | 1
Forgot Password Functionality | Create forgot password page (UI/UX) |  |  | 2
| Implement backend functionality (email integration, token reset) |  |  | 3
| Error handling (invalid email, expired token) |  |  | 1
ACL (Access Control List) | Define user roles (Admin, Sales, Customer) |  |  | 2
| Set up role-based access control (RBAC) |  |  | 2
| Implement permissions for each role |  |  | 2
Authentication & Authorization Testing | Test login, role-based access, and permissions |  |  | 2
Phase 2: Enquiry Management and Quotation Features
Task | Sub-Task | Start Date | End Date | Duration (Days)
Enquiry Form Development | Design and implement enquiry form (UI/UX) |  |  | 3
| Define fields: project details, customer info, requirements |  |  | 2
| Implement validation for fields |  |  | 1
| Implement file upload functionality (project documents) |  |  | 2
| Store data in the database |  |  | 1
| Send confirmation email to customer after submission |  |  | 1
Quotation Preparation: Costing Sections | Design and implement quotation form (UI/UX) |  |  | 2
| Create dynamic costing sections (labor, materials, etc.) |  |  | 2
| Implement validation for each costing section |  |  | 2
Draft and Save Option for Quotations | Implement "Save as Draft" functionality |  |  | 2
| Implement autosave feature |  |  | 2
| Store drafts with "draft" status in the database |  |  | 1
Report Generation | Design and implement PDF layout for quotation report |  |  | 2
| Implement PDF generation from the quotation form |  |  | 3
Phase 3: Admin Approval and Workflow
Task | Sub-Task | Start Date | End Date | Duration (Days)
Admin Approval Workflow | Design admin dashboard for review and approval |  |  | 3
| Implement approval/rejection buttons |  |  | 2
| Add comment/feedback functionality for admins |  |  | 1
Automatic Sending of Approved Reports | Implement automatic email sending after approval |  |  | 2
| Integrate email service and send PDF reports |  |  | 2
User Management Enhancements | Design user management interface for Admin |  |  | 2
| Implement Add/Edit/Delete user functionality |  |  | 2
| Assign/Modify user roles and permissions |  |  | 1
Notification System | Design and implement email notifications for important actions |  |  | 2
| Implement in-app notifications (optional) |  |  | 2
Phase 4: Dashboard & Analytics
Task | Sub-Task | Start Date | End Date | Duration (Days)
Dashboard Design and Development | Design dashboard layout (UI/UX) |  |  | 3
| Implement graphs and charts (e.g., Chart.js, D3.js) |  |  | 3
| Display statistics for enquiries and follow-ups |  |  | 3
Follow-up Tracking System | Implement follow-up tracking interface |  |  | 3
| Allow logging of follow-up actions |  |  | 2
| Implement follow-up reminders and overdue notifications |  |  | 2
Analytics for Enquiries | Implement data aggregation for enquiry statistics |  |  | 2
| Display conversion rates and other KPIs |  |  | 2
Phase 5: Testing, QA, and Deployment
Task | Sub-Task | Start Date | End Date | Duration (Days)
Unit Testing | Write unit tests for critical features (login, form submission) |  |  | 3
Integration Testing | Test end-to-end workflows (from enquiry submission to report generation) |  |  | 3
User Acceptance Testing (UAT) | Conduct UAT with stakeholders (Admin, Sales, Customer) |  |  | 3
Bug Fixing and Optimization | Address bugs from testing phase and optimize code |  |  | 3
Deployment to Production | Deploy to production environment |  |  | 2
Phase 6: Post-Launch Support and Maintenance
Task | Sub-Task | Start Date | End Date | Duration (Days)
Monitor System Performance | Monitor server and application performance |  |  | 7
Bug Fixes & Updates | Fix any issues reported post-launch |  |  | 5
User Training and Documentation | Create user guides for Admin, Sales, and Customer |  |  | 3